90-DAY ACTION PLAN (1st Semester)

District:     Richmond County Schools

School:      Glenn Hills High School

Principal:  Dr. Johnnie M. Wright

The 90-Day Plan serves as a road map that provides clarity to specific priorities and actions that are most important during the next 90 days.  The plan will help ensure the focus of all stakeholders toward an aligned understanding of the implementation and progress of our school’s transformation initiative.

PURPOSE OF THE TRANSFORMATION INITIATIVE:  Articulate in a few sentences what you hope to achieve by participating in the transformation initiative.

Within the next 90 days we hope to see an increase in teachers’ cross curriculum collaboration and usage of data during the instructional planning process. Also, we hope to see a decrease in the number of discipline referrals that are occurring during the instructional periods and when students transition in the halls. Finally, within the next 90 days we hope to establish a baseline measurement of the percentage of students who are identifying as being proficient on their most recent reading and math progress monitoring/benchmark assessments

GOAL SETTING:  Along with Language Arts and Math proficiency rates, identify up to three additional goals for the school year (i.e. graduation rate, promotion rate, attendance, discipline, growth/value-added, targeted sub-group, college readiness, etc.)

|  | Goals | 2018-19 RESULTS | 2020-21 GOALS | GOAL INDICATORS (METRIC TO INDICATE PROGRESS) |
| --- | --- | --- | --- | --- |
| 1 | Literacy and Math Proficiency |  | For FY 21, GHHS will implement data driven best practices and rigorous instructional strategies aimed at a 15% increase in the number of 9th grade students who score proficient on the EOY I-Ready (ELA/Math) as compared to the BOY I-Ready. | 65% of students taking the mid-year I-Ready benchmark and Reading Inventory will demonstrate a 10% increase in their mid-year score as compared to their beginning of the year score. |
| 2 | Collaborative Planning | Emerging Level as rated by the GaDOE Collaborative Planning Rubric. | Operational Level as rated by the GaDOE Collaborative Planning Rubric. | For the FY 21, GHHS will increase its rating from being identified as that of “emerging” to that of “operational” as rated by the GaDOE Collaborative Planning Rubric. |
| 3 | Climate & Culture | Star Rating of 1 2018-2019 ISS % OSS %: | Star Rating of 3 2019-2020 ISS % OSS %: | For the FY 21, GHHS will decrease the number of behavior infractions from FY20 by 15% through the implementation of a Positive Behavior Intervention and Support (PBIS) initiative. |

Principal Commitment:  My signature indicates that this plan provides focus and urgency to move the transformation initiative forward – and that the school’s leadership team participated in the development of the plan and support its direction.  My signature also indicates a commitment to ambitiously pursue the articulated goals, addressing priorities, and monitoring progress.  Finally, my signature confirms that this plan is a living document and that adjustments will likely be needed based on ongoing data and lessons learned.

______________________________________________________________	___________________________________________

Principal Signature									Date

Principal Supervisor Commitment:  My signature indicates that this plan has been reviewed and the content of the plan is aligned with the needs of the school.  My signature confirms a commitment to support the school in the implementation of this plan, while also holding the school’s leader accountable for its implementation.

______________________________________________________________	___________________________________________

Principal Area Superintendent Signature								Date

90-Day Action Plan:  Initiative 1 (Literacy and Math)

| Which District Strategic Goal Area is Being Addressed: Student Achievement and Success |  |  |  |  |
| --- | --- | --- | --- | --- |
| School’s Priority: Student motivation, Low deficit areas in reading and math, low proficiency percentages on the EOY I-Ready and RCSS benchmark assessments. |  |  |  | School Leader Responsible: Valeria Smith |
| Desired Outcome: (What will be different if you are successful in addressing this priority?) Show a 15% increase in the number of students who score proficient on the EOY I-Ready (ELA/Math) as compared to the BOY I-Ready. |  |  |  |  |
| Root Cause(s) to Address Hypothesis of Priority: 2018-2019 I-Ready EOY data results (ELA/Math) 2018-2019 GMAS EOC Data 2018-2019 Student Lexile Scores 2019-2020 Reading Inventory |  |  |  |  |
| ACTIONS |  |  |  |  |
| Critical Action to Address Root Cause & Achieve Desired Outcome |  | Person Completing Action | Timeline | Resources Needed / Source |
| Provide professional development and training module on CANVAS (module construction, video embedding, assignment creation, quiz/assessment construction, teacher resource integration, etc.) |  | Ms. Hall/Smith | August-December 2020 |  |
| Provide professional development and training on creating rigorous literacy based assignments and assessments aligned to all content areas |  | Ms. Hall/Smith | November 2020 |  |
| Provide professional development and training on creating rigorous numeracy based assignments and assessments aligned to all content areas |  | Ms. Hall/Smith | November 2020 | $0 |
| Facilitate and observe the implementation of rigorous literacy based assignments and assessments to all content areas |  | Ms. Hall/Smith | November 2020 | $0 |
| Facilitate and observe the implementation of rigorous numeracy based assignments and assessments to all content areas. |  | Ms. Hall/Smith | November 2020 |  |
| Establish procedures and engage in data analysis protocols that look at student performance and assessments alignment utilizing the Tuning Protocol. |  | Wright/Smith | December 2020 | $0 |
| Develop peer observation schedule to be utilized by Leadership Team members on a rotating basis twice per month. |  | Wright/Smith | October 2020 | $0 |
| Develop walk-through schedule for administrative use with district, RESA, and State personnel. |  | Wright/Smith | October 2020 |  |
| Each content will create a minimum of two (2) common assessments aligned to our district pacing guide per grading period to be administered and scored using the tools in Canvas |  | Wright/Smith | November-December 2020 |  |
| PROGRESS INDICATORS |  |  |  |  |
| Indicator Date | Evidence to Determine Progress Toward Achieving Desired Outcome |  | Potential Adjustments |  |
| Weekly | Collaborative planning sign in sheets, PLC sign in sheets, Lesson plans |  | Restructuring may be necessary based on the data gathered. Frequency of meetings may be needed |  |
| Weekly | Administrative Feedback on lesson plans and assessments. |  |  |  |
| January 2021 | District Quarterly Assessment & 1st Semester Final Exam Results Analyzed |  | Lesson Planning/Assessment Creation |  |
| January 2021 | Weekly Wednesday/Thursday Turning Protocols Sign In Sheets, Videos, Feedback, Observations |  | Lesson Planning/Assessment Creation |  |
| October 2020 | I-Ready benchmark window ends. Results will be analyzed. |  | Lesson plan/tuning. |  |

90-Day Action Plan:  Collaborative Planning

| Which District Strategic Goal Area is Being Addressed: High Performing Culture and Workforce |  |  |  |  |
| --- | --- | --- | --- | --- |
| School’s Priority: (Given the goals identified, what problem needs to be addressed to achieve these goals?) Create Succession in Planning |  |  |  | School Leader Responsible: Dr. Johnnie Wright/Valeria Smith |
| Desired Outcome: (What will be different if you are successful in addressing this priority?) Over the course of the 2020-2021 school year all GHHS teachers will engage in weekly collaborative planning and tuning sessions that address research-based best practices to include student engagement, student performance, rigor, and differentiation at the operational level as defined by the GADOE Impact Rubric. |  |  |  |  |
| Root Cause(s) to Address Hypothesis of Priority: (What do you believe is at the heart of this problem? What evidence do you have to support this hypothesis?) A lack of consistency in monitoring the collaborative planning process and in reviewing lesson plans submitted for implementation have greatly contributed to the problem. The evidence that we have to support this hypothesis is data from the collaborative planning audit and teacher feedback via survey. |  |  |  |  |
| ACTIONS |  |  |  |  |
| Critical Action to Address Root Cause & Achieve Desired Outcome |  | Person Completing Action | Timeline | Resources Needed / Source |
| Establish a collaboration planning schedule/calendar for hosting face to face or virtual collaborative planning sessions. |  | Mrs. Hall/Ms. Smith | September 2020 |  |
| Establish collaboration planning teams & team leaders and tuning roles. |  | Mrs. Hall/Ms. Smith | September 2020 |  |
| Develop protocols and norms for collaborative planning for face to face or virtual collaborative planning sessions. |  | Dr. Wright/Ms. Smith | October 2020 | $0 |
| Revise the collaborative planning template that includes reflective questions and digital learning opportunities for students. |  | Mrs. Hall/Ms. Smith | September 2020 | $0 |
| Provide ongoing professional learning sessions on the following topics: Canvas, Maps, Turn it In, Revision Assistant, Teams, Pearson (textbooks), Zooms, Google Classroom, Texas Instrument TI-84 calculators |  | Mrs. Hall/Ms. Smith | September-December 2020 | $0 |
| Develop differentiated lessons/ instructional strategies utilizing the tools found in Canvas and the RCSS Launchpad. |  | Mrs. Hall/Ms. Smith | September-December 2020 | $0 |
| PROGRESS INDICATORS |  |  |  |  |
| Indicator Date | Evidence to Determine Progress Toward Achieving Desired Outcome |  | Potential Adjustments |  |
| September-December 2020 | Collaborative planning sign in sheets, lesson plans |  |  |  |
| January 2020 | Collaborative planning mid-year audit findings |  |  |  |
| October-December 2020 | Tuning Protocol sign-in sheets, lesson plans, pictures, surveys |  |  |  |

90-Day Action Plan:  Non-Academic/Climate & Culture Priority

| Which District Strategic Goal Area is Being Addressed: Operational Effectiveness |  |  |  |  |
| --- | --- | --- | --- | --- |
| School’s Priority: (Given the goals identified, what problem needs to be addressed to achieve these goals?) School-wide Discipline, Attendance, Teacher Retention |  |  |  | School Leader Responsible: Derrias Priestley/Silburn Pitter |
| Desired Outcome: (What will be different if you are successful in addressing this priority?) For the FY 21, GHHS will decrease the number of behavior infractions from FY19 by 15% through the implementation of a Positive Behavior Intervention and Support (PBIS) initiative. |  |  |  |  |
| Root Cause(s) to Address Hypothesis of Priority: (What do you believe is at the heart of this problem? What evidence do you have to support this hypothesis?) Lack or processes and procedures, poor data input, failure to follow district protocol, poor student and adult efficacy. The data that we have to support this hypothesis is 2018-2019 school wide discipline data (OSS/ISS/Infraction percentages), 2018-2019 attendance data, 2018-2019 Health Survey feedback. |  |  |  |  |
| ACTIONS |  |  |  |  |
| Critical Action to Address Root Cause & Achieve Desired Outcome |  | Person Completing Action | Timeline | Resources Needed / Source |
| Teachers As Advisors: Develop a refined protocol for TAA sessions and continue to monitor. Allow for grade level teacher communication. |  | Dr. Johnnie Wright/Crecia Vaughn | October 2020 | $0 |
| Conduct SWIS Training for PBIS team and Registrar. |  | Mr. Pitter | October 2020 | $0 |
| Develop weekly mentor/mentee "check-in" and assignment of "follow-up" plan on designated tasks to be recorded in shared OneDrive folder and monitored and supported by the Glenn Hills High School administrative team. |  | Mrs. Hall/Ms. Smith | September 2020 |  |
| Develop GHHS PBIS Matrix and posters |  | Mr. Pitter/S. Donigan | October 2020 | $0 |
| Develop PBIS committee schedule of meetings and initiatives. |  | Mr. Pitter/S. Donigan | October 2020 | $0 |
| Develop monthly student recognition calendar of events |  | Mr. Pitter/K. Cunningham | September-December 2020 | $0 |
| PROGRESS INDICATORS |  |  |  |  |
| Indicator Date | Evidence to Determine Progress Toward Achieving Desired Outcome |  | Potential Adjustments |  |
| Monthly | Attendance committee meeting schedule and reports |  |  |  |
| Monthly | SWIS/Infinite Campus Behavior Data |  |  |  |
| Monthly | School wide student recognition calendar of events (published) |  |  |  |
| Monthly | TAA Lessons |  |  |  |