2017-2018 School Improvement Plan – Elementary

School:  T. Harry Garrett Elementary School			 Principal: Stacey M. Walk		 Date:  October 2, 2017

| Performance Measure (with unit of measure) | Baseline (2015-2016) | Target Year 1 (2016-2017) | Actuals Year 1 (2016-2017) | Target Year 2 (2017-2018) | Actuals Year 2 (2017-2018) | Target Year3 (2018-2019) | Actuals Year 3 (2018-2019) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Increase the percentage of students reading on grade level by Grade 3 (Proficient or above on the Grade 3 Georgia Milestones ELA EOG) | 11% | 12.1% | 15.2% | 16.7 |  | 18.4% |  |
| Increase the percentage of students scoring Proficient or above on the Grade 4 Georgia Milestones Mathematics EOG | 20% | 22% | 31.8% | 35% |  | 38.5% |  |
| Increase the percentage of 5th grade students scoring Proficient or above on the Science EOG | 15.5% | 17.1% | 9% | 10% |  | 11% |  |
| Increase the percentage of 5th grade students scoring Proficient or above on the Social Studies EOG | 2% | 2.2% | 8.7% | 9.6% |  | 10.56% |  |
| Increase the school’s CCRPI Target | 41.4 | 45.5 | 60.6 | 50.1 |  | 55.1 |  |
| Principal's Signature School Council's President's Signature Leadership Team Member Leadership Team Member |  |  |  |  |  |  |  |

Goal Area:   _Operational Effectiveness_______________________	________________________

Performance Objective:  Establish and Monitor Policies and Procedures for Effectiveness

Initiative:  __Policies, procedures, and a high performing school culture will be developed, implemented, and monitored from August 2017 to May 2018 ______________________________________________________________________________________

| Group Affected by Initiative | Research-Based Action Steps ) | Team or Leader who will oversee the initiative and actions & collect data (LOOK AND DELEGATE WORK) | Data that the Team or Leader will collect (HOW WILL THIS MONITORED) | Timeline for implementing initiative and actions | Funding Source, Materials/Resources Needed |
| --- | --- | --- | --- | --- | --- |
| Faculty, Staff, Parents, Guardians | Write a process for: Collaborative Planning, School Opening and Dismissal Process, and Intervention. | Administration and Leadership Team | The written processes and procedures, Title 1 Survey from BOY to EOY | August 2017 – November 2017 | N/A |
| Students | Provide incentives for students with excellent behavior and perfect attendance monthly. | Coach Williams Teachers, Attendance Committee | Attendance Behavior (Track in Infinite Campus) | August 2017 – May 2018 | $1,000.00 |
| Faculty and Staff | Notify teachers of attendance concerns; provide incentives for faculty and staff with perfect attendance monthly. | Administration | Absence Management Reports | August 2017 – May 2018 | N/A |
| PreK through 5th Grade | Create, implement, and monitor writing area. (Garrett Post Office) | Coach Williams | Writing Samples | August 2017 – May 2018 | N/A |

Goal Area:   High Academic Achievement and Success for All

Performance Objective:  Increase student performance at or above grade level

Initiative:  K – 5th grade students will perform at or above grade level in ELA/Reading and Math

| Group Affected by Initiative | Research-Based Action Steps | Team or Leader who will oversee the initiative and actions & collect data | Data that the Team or Leader will collect | Timeline for implementing initiative and actions | Funding Source, Materials/Resources Needed |
| --- | --- | --- | --- | --- | --- |
| K – 5th Grade Students | Purchase computers and carts for students to utilize I-Ready and other academic internet software. | Administration Technology Committee, Media Specialist | # of computers working at GES | August 2017 – May 2018 | $13,757.00 |
| K – 5th Grade Students | Peer Observations: Teachers will observe other classrooms for ideas and instructional strategies. | Administration Instructional Coach | I-Ready Data, GMAS Data, Accelerated Reader | August 2017 – May 2018 | N/A |
| K – 5th Grade Students | Teachers will utilize strategies from PL called Writing Across the Curriculum with Dr. Rebecca Harper. | Administration Instructional Coach | I-Ready Data, GMAS Data, Accelerated Reader, Lesson Plans, Observation | September 2017 – March 2018 | $7,000.02 |
| K – 5th Grade Students | Teachers will attend the Rigor and Relevance Training from BOE PL | Administration Instructional Coach | I-Ready Data, GMAS Data, Accelerated Reader, Lesson Plans, Observation | August 2017 – October 2017 | N/A |
| K – 5th Grade Students | Teachers will utilize the strategies given during the Rigor and Relevance Training with their students. | Administration | I-Ready Data, GMAS Data, Accelerated Reader, Lesson Plans, Observation | August 2017 – May 2018 | N/A |
| K – 5th Grade Students | Purchase and utilize Accelerated Reader to increase Lexile Levels and Brain Pop to support instruction. | Administration, Teachers, Media | I-Ready Data, GMAS Data, Accelerated Reader | August 2017 – May 2018 | $4,893.00 |

Goal Area:   Community Engagement

Performance Objective:  Pursue and Attract Collaborative Partnerships

Initiative:  Garrett Elementary will increase our school partnerships by 10% or more by May of 2018

| Group Affected by Initiative | Research-Based Action Steps | Team or Leader who will oversee the initiative and actions & collect data | Data that the Team or Leader will collect | Timeline for implementing initiative and actions | Funding Source, Materials/Resources Needed |
| --- | --- | --- | --- | --- | --- |
| Faculty, Staff, Students, Parents, and Guardians | Actively seek partnerships from local business and restaurants to help sponsor school events such as attendance incentives, game nights, fall carnivals, Red Ribbon week and Title 1 events. | Administration | Number of business and restaurants that participated with our school. | August 2017 – May 2018 | N/A |
| Faculty, Staff, Students, Parents, and Guardians | Schedule Title 1 events that will include partnerships such as Comcast, Whole Life Ministries, and Augusta Public Library | Administration | Number of Title 1 Events and businesses that attended the events | August 2017 – May 2018 | N/A |
| Faculty, Staff, Students, Parents, and Guardians | Have local businesses partner with our Arts Department to help our students to see real life applications of the Arts. | Administration | Number of local businesses that partnered with our Arts Department. | August 2017 – May 2018 | N/A |

Professional Learning Plan to Support School Improvement Plan

| Professional Learning Strategy to Support School Improvement Plan Initiative | Professional Learning Timeline | Estimated Cost, Funding Source, and/or Resources | Person(s)/ Position Responsible | Monitoring Teacher Implementation of Professional Learning | Artifacts/Evidence of Impact on Student Learning |
| --- | --- | --- | --- | --- | --- |
| Writing Across the Curriculum Dr. Rebecca Harper | September 2017 – March 2018 | $7,000.02 | Administration Instructional Coach | Administration Instructional Coach | I-Ready Data GMAS Data Student Work |
| Subs for one day of half day training for Writing Across the Curriculum Dr. Rebecca Harper | September 2017 | $825.00 | Administration Instructional Coach | Administration Instructional Coach | I-Ready Data GMAS Data Student Work |
| Professional Learning: Book By Dr. Harper: Writing Across the Curriculum | September 2017 – March 2018 | $625.00 | Administration | Administration Instructional Coach | I-Ready Data GMAS Data Student Work |
| Professional Learning: Rigor and Relevance Training PL from the BOE | October 2017 | N/A | Administration | Administration Instructional Coach | I-Ready Data GMAS Data Student Work |

| Parental Involvement Plan to Support School Improvement Plan Parent Engagement Activities | Person(s) Responsible- will oversee the actions | Evaluation Results | Evidence of Impact on Student Learning | Timeline | Estimated Cost, Funding Source, and/or Materials/Resources Needed |
| --- | --- | --- | --- | --- | --- |
| Host meetings: *Annual Title I Meeting *Review/Revision- Policy, Compact, SIP/SWP/TA Plan, & PI Budget, *Volunteer Training *Parent/Teacher Conferences | Dr. Lutricia Parkman Dr. Beth Powell | Parent Evaluation Questionnaires at the end of sessions | I-Ready GMAS Student Work | September 2017 – May 2018 | N/A |
| Provide: Materials/Explanation *Information @ Title I *Curriculum *Academic Assessments *Proficiency Levels/Progress Monitoring Results *School Status *School Policy &Compact *RTK *Complaint Procedures | Dr. Lutricia Parkman Dr. Beth Powell | Parent Evaluation Questionnaires at the end of sessions | I-Ready GMAS Student Work | September 2017 – May 2018 | $2, 495.17 |

**The Title I Annual Meeting must be held before October 1st but not prior to compact and policy revisions. (Include revision date on policy)

**100% Compacts should be signed, dated, and returned before November 1st   except for new students. (Include revision date on compacts)

** All parent meetings should be maintained throughout year with complete documentation (sign in agendas, handouts, webpage posting, shout points, etc.